## Sprint 1
|  |  | Estimation (hr) | Totally 100 hrs
1 | DB
| 1.1. | Create New DB
| 1.2. | Prepare dammy data (All the data we need)
2 | .Net Solution & Demo
| 2.1. | Solution Create (with DB connect, team)
| 2.2. | Create Master page
| 2.3. | Create Demo page (css, js, aspx...)
3 | HomePage
| 3.1. | Draft version (main page + team profile + Faq)
| 3.2. | Updated version
| 3.3. | Test case (Nunit & Case)
| 3.4. | Unit Test
4 | Success stories list (Individual & Company version)
| 4.1. | Statics page design (layout, mobile-friendly)
| 4.2. | Dynamic page (aspx, using DB data)
| 4.3. | Test case (Nunit & Case)
| 4.4. | Unit Test
5 | Admin Pages(List, Add, Edit)
| 5.1. | Add page
| 5.2. | Edit page
| 5.3. | List page
| 5.4. | Test case (Nunit & Case)
| 5.5. | Unit Test
6 | Login page(.Net)
| 6.1. | Login Page
| 6.2. | Test case (Nunit & Case)
| 6.3. | Unit Test