## Task List(sprint2)
Story ID | User Story | Task ID | Task | Owner & Participant | UPI | Hours
1 | Refine Home Page | 11 | Change carousel to success story & Height | ClayY | cyan988 | 5
| Refine Home Page | 12 | Website statistics | Irene | ygao742 | 3
| Refine Home Page | 13 | Test for carousel | Shawn | syu702 | 2.5
| Refine Home Page | 14 | Test for websit statistics | LikaiH | lhe838 | 1.5
2 | Refine Success Story (List & Detail) | 21 | Share icons for social media | Shawn | syu702 | 6
|  | 22 | Refine success story list page | Lulu | jlu986 | 3
|  | 23 | Refine detail page | LikaiH | lhe838 | 3
|  | 24 | Test for social media shareing | Kaii | hxie519 | 3
|  | 25 | Test for success story list page | Kaii | hxie519 | 1.5
|  | 26 | Test for detail page | Irene | ygao742 | 1.5
3 | Team Profile Admin Function | 31 | Team profile dynamic page & Admin function | Miranda | yguo325 | 8
|  | 32 | Linkin Add-in | Shawn | syu702 | 1
|  | 33 | Test for team profile page | Kaii | hxie519 | 4
|  | 34 | Test for Linkin icon add-in | Kaii | hxie519 | 0.5
4 | Test automation page | 41 | Update description on HP and add detail page | ClayY | cyan988 | 4
|  | 42 | Test for Test automation (HP & detail) | Lulu | jlu986 | 2
5 | Contact Function | 51 | Add "contact us" function | V | vbor051 | 8
|  | 52 | Test for "contact us" function | LikaiH | lhe838 | 4
6 | Google Search Keyword | 61 | Google searching keywork | Irene | ygao742 | 4
X1 | Scrum Activities | 1 | Sprint meeting | ALL members |  | 8
|  | 2 | Daily scrum (09/23) | ALL members |  | 4
|  | 4 | Daily scrum (10/02) | ALL members |  | 4
|  | 5 | Daily scrum (10/04) | ALL members |  | 4
|  | 6 | Daily scrum (10/05) | ALL members |  | 4
|  | 3 | Client Review (10/01) | ALL members |  | 3
|  | 7 | Client Review (02) | ALL members |  | 3
|  | 8 | Scrum Review meeting | ALL members |  | 6