## Task List
Story ID | User Story | Task ID | Task | Owner & Participant | UPI | Hours
1 | Home Page | 31 | Home Draft | ClayY |  | 8
|  | 32 | Home Page Update (after review) |  |  | 8
|  | 33 | Test Case (HP) | Irene |  | 1
|  | 34 | Unit Test (HP) | Irene |  | 1
2 | Success Story List | 41 | Story List (staic) | LikaiH |  | 10
|  | 42 | Story List (dynamic) | ClayY |  | 8
|  | 43 | Test Case (Story List) | Lulu |  | 4
|  | 44 | Unit Test (Story List) | Irene |  | 1
3 | Success Story Detail | 45 | Detail Success Story Page | ClayY |  | 4
|  | 46 | Test Case (Story Detail) |  |  | 3
|  | 47 | Unit Test (Story Detail) |  |  | 2
4 | Team Profile & FAQ | 48 | Team profile page | ClayY |  | 2
|  | 49 | FAQ page | LikaiH |  | 2
5 | Admin of Success Story | 51 | Admin (List page) | Kaii |  | 9
|  | 52 | Admin (Edit page) | Kaii |  | 8
|  | 53 | Admin (Add page) | V |  | 7
|  | 53 | Admin (Add page) | Kaii |  | 1
|  | 54 | Test Case & NUnit (Add) | Miranda |  | 4
|  | 55 | Test Case & NUnit (Edit) | Miranda |  | 4
|  | 56 | Test Case & NUnit (List) | Lulu |  | 4
|  | 57 | Unit Test (Story Detail) | Lulu |  | 3
|  | 58 | Admin (Delete page) | Kaii |  | 3
x1 | Developing Enviroment | 11 | Collect DB Design and PHP programs | V |  | 2
|  | 12 | Create New DB | V |  | 2
|  | 12 | Create New DB | Miranda |  | 1
|  | 13 | Prepare dummy Data | V |  | 1
|  | 13 | Prepare dummy Data | Miranda |  | 3
|  | 21 | Create .Net solution | Shawn |  | 4
|  | 22 | Create header & Footer template | Shawn |  | 6
|  | 23 | Create base page | Shawn |  | 15
|  | 61 | Login Page | Miranda |  | 6
|  | 62 | Test Case & Nunit (Login) | Irene |  | 4
|  | 63 | Unit Test (Login) | Irene |  | 1
x2 | Scrum Activities | 1 | Client Meeting(25/08/2015) | ALL members |  | 4
|  | 2 | Scrum board init | Kaii |  | 1
|  | 3 | Draft tasks list | Kaii |  | 1
|  | 91 | Daily Scrum (28/08/2015) | ALL members |  | 1
|  | 92 | Daily Scrum (02/09/2015) | ALL members |  | 1
|  | 93 | Daily Scrum (05/09/2015) | ALL members |  | 1
|  | 94 | Daily Scrum (08/09/2015) | ALL members |  | 1
|  | 95 | Daily Scrum (11/09/2015) | ALL members |  | 1
|  | 96 | Retrospective Meeting | ALL members |  | 4
|  | 97 | Client review Meeting(14/09/2015) | ALL members |  | 6
|  | 98 | Client review Meeting(14/09/2015) | ALL members |  | 2

## Scoure Code
│ GetSkills.sln
│
├─.vs
│ ├─config
│ │ applicationhost.config
│ │
│ └─GetSkills
│ └─v14
├─GetSkills
│ │ GetSkills.csproj
│ │ GetSkills.csproj.user
│ │ Global.asax
│ │ Global.asax.cs
│ │ packages.config
│ │ Readme.html
│ │ Startup.cs
│ │ Web.config
│ │ Web.Debug.config
│ │ Web.Release.config
│ │
│ ├─App_Data
│ │ aspnet-GetSkills-20150910113325.mdf
│ │ aspnet-GetSkills-20150910113325_log.ldf
│ │
│ ├─App_Start
│ │ BundleConfig.cs
│ │ FilterConfig.cs
│ │ IdentityConfig.cs
│ │ RouteConfig.cs
│ │ Startup.Auth.cs
│ │
│ ├─bin
│ │ │ | …
│ │
│ ├─Content
│ │ │ bootstrap.css
│ │ │ bootstrap.min.css
│ │ │ carousel.css
│ │ │ font-awesome.css
│ │ │ font-awesome.min.css
│ │ │ general.css
│ │ │ login.css
│ │ │ login2.css
│ │ │ Site.css
│ │ │
│ │ └─dist
│ │ └─css
│ │ bootstrap-theme.css
│ │ bootstrap-theme.css.map
│ │ bootstrap-theme.min.css
│ │ bootstrap.css
│ │ bootstrap.css.map
│ │ bootstrap.min.css
│ │ dashboard.css
│ │ main.css
│ │
│ ├─Controllers
│ │ AccountController.cs
│ │ HomeController.cs
│ │ ManageController.cs
│ │ SuccessStoryController.cs |  | Kaii
│ │
│ ├─fonts
│ │ fontawesome-webfont.eot
│ │ fontawesome-webfont.svg
│ │ fontawesome-webfont.ttf
│ │ fontawesome-webfont.woff
│ │ fontawesome-webfont.woff2
│ │ FontAwesome.otf
│ │ glyphicons-halflings-regular.eot
│ │ glyphicons-halflings-regular.svg
│ │ glyphicons-halflings-regular.ttf
│ │ glyphicons-halflings-regular.woff
│ │
│ ├─images
│ │ │ | …
│ │
│ ├─Models
│ │ AccountViewModels.cs
│ │ board.cs
│ │ category.cs
│ │ CategoryCheckBoxModel.cs |  | Kaii
│ │ class.cs
│ │ class_students.cs
│ │ client_details.cs
│ │ contact_us.cs
│ │ content.cs
│ │ course.cs
│ │ CourseCheckboxModel.cs |  | Kaii
│ │ courses_category.cs
│ │ courses_sort_order.cs
│ │ CourseViewModel.cs
│ │ course_price.cs
│ │ demo_requests.cs
│ │ email.cs
│ │ email_group_contacts.cs
│ │ GetSkills.Context.cs
│ │ GetSkills.Context.tt
│ │ GetSkills.cs
│ │ GetSkills.Designer.cs
│ │ GetSkills.edmx
│ │ GetSkills.edmx.diagram
│ │ GetSkills.tt
│ │ grade.cs
│ │ IdentityModels.cs
│ │ interview.cs
│ │ interview_schedules.cs
│ │ interview_students.cs
│ │ manager_details.cs
│ │ ManageViewModels.cs
│ │ mapping.cs
│ │ mapping_subjects.cs
│ │ newemailgroup.cs
│ │ order_days.cs
│ │ order_subjects.cs
│ │ payment_log.cs
│ │ permission.cs
│ │ question_answers.cs
│ │ Repository.cs
│ │ specialization.cs
│ │ StoryCategoryViewModel.cs |  | Kaii
│ │ StoryCourseViewModel.cs |  | Kaii
│ │ StoryIndexViewModel.cs |  | Kaii
│ │ student_courses.cs
│ │ student_details.cs
│ │ student_orders.cs
│ │ student_subject_details.cs
│ │ subject.cs
│ │ success_story.cs |  | Kaii
│ │ success_story_category.cs
│ │ success_story_courses.cs
│ │ teacher_details.cs
│ │ teacher_subject_details.cs
│ │ teammember.cs
│ │ test.cs
│ │ test_attempts.cs
│ │ test_attempt_details.cs
│ │ test_questions.cs
│ │ topic.cs
│ │ uploadtest.cs
│ │ user.cs
│ │ users_permissions.cs
│ │ user_emails.cs
│ │ video.cs
│ │
│ ├─obj
│ │ └─ …
│ │
│ ├─Properties
│ │ │ AssemblyInfo.cs
│ │ │
│ │ └─PublishProfiles
│ │ GetSkills.pubxml
│ │ GetSkills.pubxml.user
│ │
│ ├─Scripts
│ │ bootstrap.js
│ │ bootstrap.min.js
│ │ holder.min.js
│ │ ie-emulation-modes-warning.js
│ │ ie10-viewport-bug-workaround.js
│ │ jquery-1.10.2.intellisense.js
│ │ jquery-1.10.2.js
│ │ jquery-1.10.2.min.js
│ │ jquery-1.10.2.min.map
│ │ jquery.min.js
│ │ jquery.validate-vsdoc.js
│ │ jquery.validate.js
│ │ jquery.validate.min.js
│ │ jquery.validate.unobtrusive.js
│ │ jquery.validate.unobtrusive.min.js
│ │ modernizr-2.6.2.js
│ │ respond.js
│ │ respond.min.js
│ │ _references.js
│ │
│ ├─StaticPages
│ │ footer.html
│ │ header.html
│ │ index.html
│ │ login.html
│ │ login2.html
│ │ success story main - 副本.html
│ │ successstory.html
│ │ successstorymain.html
│ │ test.html
│ │
│ └─Views
│ │ Web.config
│ │ _ViewStart.cshtml
│ │
│ ├─Account
│ │ AdminLogin.cshtml
│ │ ConfirmEmail.cshtml
│ │ ExternalLoginConfirmation.cshtml
│ │ ExternalLoginFailure.cshtml
│ │ ForgotPassword.cshtml
│ │ ForgotPasswordConfirmation.cshtml
│ │ Login.cshtml
│ │ Register.cshtml
│ │ ResetPassword.cshtml
│ │ ResetPasswordConfirmation.cshtml
│ │ SendCode.cshtml
│ │ VerifyCode.cshtml
│ │ _ExternalLoginsListPartial.cshtml
│ │
│ ├─Home
│ │ About.cshtml
│ │ Contact.cshtml
│ │ Create.cshtml
│ │ FAQ.cshtml
│ │ Index.cshtml
│ │ TeamProfile.cshtml
│ │
│ ├─Manage
│ │ AddPhoneNumber.cshtml
│ │ ChangePassword.cshtml
│ │ Index.cshtml
│ │ ManageLogins.cshtml
│ │ SetPassword.cshtml
│ │ VerifyPhoneNumber.cshtml
│ │
│ ├─Shared
│ │ Error.cshtml
│ │ _Layout.cshtml
│ │
│ └─SuccessStory
│ Create.cshtml |  | V, Kaii
│ Delete.cshtml |  | Kaii
│ Detail.cshtml |  | Kaii
│ Edit.cshtml |  | Kaii
│ Index.cshtml |  | Kaii
│ List.cshtml
│
├─GetSkills.Tests
│ │ App.config
│ │ GetSkills.Tests.csproj
│ │ packages.config
│ │
│ ├─bin
│ │ └─ …
│ │
│ ├─Controllers
│ │ AccountControllerTest.cs
│ │ HomeControllerTest.cs
│ │ ManageControllerTest.cs
│ │ SuccessStoryControllerTests.cs
│ │
│ ├─obj
│ │ └─ …
│ └─Properties
│ AssemblyInfo.cs
│
├─packages
│ └─ …
│
└─TestResults