## Risk Plan
[12 empty] | 1 | Others
| Risk Identification |  |  |  |  | Risk Mitigation |  |  | Risk Tracking |  |  | 2
S.No | Category | Description | Impact Description | Level of Impact | Probability | Action | Responsibility | Target Date | Current Probability | Current Impact | Status of Mitigation Action | 4
1 | Technical | Most of our team members are not familiar with web/mobile development. | 1. Extral effort should be used for trainning, review and seeking help. 2. Sysytem architecture and design will be focused on skilled members. But there is works in progress (WIP). 3. 2-week sprint may be short to catch up the required skills and tasks should be done within it. | Very High | Very High | 1. Every member should try herself/himself to catch up the skills and focus on some details which are needed for our project. 2. Make demo for team to understand and follow the standard. 3. Pair programming. | All Team Members | 2015-08-22 | Very High | Medium | In Progress | 5
2 | Requirement | The initial requirements have be changed completely. New requirements are still not steable. | 1. It would effect our Sprint Planning, as well as the following design workshop and system architecture. 2. Our team may asked to prepare user stories and propose them for confirm, which can delay our schedule. | High | High | 1. Prepare our user stories and push our customers to confirm and set the priorities for them. 2. Try to prive more technology and detail business needs to guide our client to adapt our proposes. | All Team Members | 2015-08-18 (for 1#. U.S.) | Very High | High | In Progress | 5
3 | Technical | Web service and DB design may not be available. | 1. We have to image the stucture of DB data and prepare dumy data for development and test. 2. The technology/skill sets used may be different, that may result in less value of our product. | Medium | High | 1. Ask for design documentation of DB or web services of future system. 2. In case of prepareing dumy data, confirm the data structure in sprint planning. | All Team Members | 2015-08-22 | Medium | Low | Not Start
4 | Others | Individual English skills may affect our communication and design. | 1. There may be some misunderstanding. 2. More efforts are required to check our documentation. | Low | Medium | 1. Use LIGHT document. 2. Use more chart, table and graph to documentate our design. 3. Ask others for review. | All Team Members | on going | Low | Medium | Not Start
5
6
7
8
9
10

## Help
Risk Identification :
This section lists the risks involved in the project. The following could be some broad Risk categories and subcategories to be considered at the time of risk planning.
1. Cost Risks
a. Estimating errors
b. Overruns to unplanned tasks such as solving technical, operational and programmatic problems
c. Scope expansion & change
2. Schedule Risks
a. Estimating errors
b. Increased effort to solve technical, operational and programmatic problems
c. Resource unavailability including staffing delays, technology maturity delays, compressed and complex critical tasks
3. Technical Risks
a. Requirement changes
b. Product complexity
c. Integration problems
d. Problems with immature technology
4. Operational Risks
a. Inadequate resolution of priority conflicts
b. Failure to clarify and resolve responsibility and authority conflicts
c. Poor or inadequate communication
d. Incomplete human resource planning
e. Poor or inadequate training
f. Insufficient or unsuitable physical resources
g. Inability of the organization to positive change
5. Programmatic Risks
a. Government regulation changes
b. Legal issues
c. Market developments
d. Funding problems
e. Customer or owner organization strategy and priority changes
f. Other influences outside the direct control of the program / project